## AllReq
id | Priority | Class | ComponentName | target | Start | End | Design | Code | Utest | Integration | Itest | Release | Status
1 |  | I&S | Integrate infile duplicate processing with Base run based of flagged instruction. | 2019-02-04 |  |  | done | done | done | open | open | open | open
2 |  | F&E | Include direct map input in logic file for useMap for simple one to one correspondence. | 2019-02-04 |  |  | open | [5 empty] | open
3 |  | Opt | Implement zip read write for faster data processing. |  |  |  | open | [5 empty] | open
4 |  | Log | Analysis and Fine Tuning of Error logs. |  |  |  | done | done | done | open | open | open | open
5 | 1 | EC | Debug Error for Title setvalue for handle run. Ensuring setValue and add results. |  |  |  | open | [5 empty] | open
6 |  | F&E | Curation Class override feature at runtime. Implement Java Reflection. |  |  |  | open | [5 empty] | open
7 |  | F&E | Runtime inclusion of machine learned models. Preferrebly jar files via inputs in parameter file. |  |  |  | open | [5 empty] | open
8 | 1 | F&E | Implement dynamic key processing for json string using parseAs properties. |  |  |  | done | done | done | wip | wip | open | wip
9 | 1 | F&E | Deletion of json keys while providing parseAs properties. deleteKey action. |  |  |  | done | done | done | wip | wip | open | wip
10 |  | I&S | Config File generator. |  |  |  | open | [5 empty] | open
11 | 1 | I&S | handle based logic file generator. Python executables for generating schemaActionbyHandle and fieldTranslation csv files from excel input. |  |  |  | done | done | done | wip | wip | open | wip
12 | 3 | F&E | Deletion of items based on handle list provided. |  |  |  | open | open | open | open | open | open | open
13 | 2 | I&S | Analyser tool release |  |  |  | done | done | done | done | open | open | open
14 | 1 | F&E | Author curation to incorporate removetokens flag and its descriptors. |  |  |  | done | done | done | wip | wip | wip | wip
15 | 3 | F&E | Design render as feature. |  |  |  | open | open | open | open | open | open | open
16 | 4 | F&E | DataCuration reporting tool. Shall report impact of logics implements and to be used for data quality analysis. |  |  |  | open | [5 empty] | open
17 | 3 | F&E | Enhancing parseAs feature to accept regular expression and then storing it in array or map. |  |  |  | open | open | open | open | open | open | open
18 | 2 | F&E | Introducing dependency graph and dependency order on action commands. |  |  |  | wip | open | open | open | open | open | wip
19 | 1 | F&E | MoveField command to incorporate full feature support of token searching(startsWith, endsWith, contains, regularexpression |  |  |  | done | done | done | wip | wip | wip | wip
20 | 1 | F&E | Option to use Map File for translation or text maps for small simple value translation. |  |  |  | done | done | done | wip | wip | wip | wip
21 | 2 | Log | unmatched datatype reporting |  |  |  | open | open | open | open | open | open | open
22 | 3 | F&E | Define curation standard actions and introduction and extension of pallate. |  |  |  | wip | open | open | open | open | open | wip
23 | 2 | F&E | Introduce curation command deleteValue, moveValue
24 | 2 | F&E | Extend filter to include multiple value and operator.
25 | 1 | EC | logic file mismatch for run option to be indicated in user understandable expression instead java error.

## ReleaseLog3.2
Sl. | Feature
1 | Curation Action is based on removeTokens and Render flags. Option to choose the ADT of value.
2 | Source data can be parsed to defined datatypes or defined ADT. Then iterable over Arrays or Maps based on parsing. Source Data Can be dynamically parsed as per given requirement.